ELITE CLIENT HUB

Development Brief for AI / Software Engineer

Phase 1 — Two-Week MVP Delivery  |  Phase 2 — Full Future Scope

PHASE 1 DELIVERY WINDOW Monday 7 September 2026 — Friday 18 September 2026 Objective: Deliver a working internal MVP that can be piloted with real Elite clients immediately after the two-week build.

Prepared for Elite Tax & Wealth Advisory

# 1. Project Objective

Build a secure, mobile-friendly client workflow and communication platform that allows Elite staff and clients to see exactly where a job is, what is outstanding, who needs to act next and what progress has been made. Phase 1 is deliberately limited to the core workflow and must be completed within two weeks.

The client should not need to call Elite simply to ask, “Where is my tax return?” The system should show the answer and send progress notifications automatically.

# 2. Phase 1 — Non-Negotiable MVP Outcomes

Secure staff and client login with role-based access.

Client and entity records, including the ability to link multiple entities to one client.

Job creation and assignment to accountant and supervisor.

Nine-stage tax workflow plus On Hold and Action Required states.

Staff dashboard with filters and clear “days in stage” visibility.

Supervisor review queue.

Client portal showing simple client-facing progress, last update and next action.

Secure document upload from desktop and mobile.

Outstanding-document requests visible to clients.

Automatic email notifications when selected workflow stages change.

Basic SMS capability if technically straightforward within the two-week build; otherwise the system must be architected so SMS can be switched on immediately after the MVP.

Audit trail of status changes, uploads, assignments and client notifications.

Responsive web design; no native iPhone or Android app is required for Phase 1.

# 3. Phase 1 — Functional Scope

## 3.1 Client & Entity Database

Unique Client ID and Entity ID.

Client name, entity name, entity type, email, mobile and contact details.

Link one person/client to multiple entities such as individual, company, trust and SMSF.

Assigned accountant and assigned supervisor.

Current and historical jobs.

Current job status and date/time of last status change.

Document links and communication history.

## 3.2 Secure Authentication & Permissions

Client login.

Staff login.

Role-based permissions for Administrator, Supervisor, Accountant, Reception/Admin and Client.

Clients must never be able to view another client’s data or documents.

Password reset process and account disable function.

Session and access controls appropriate for confidential tax information.

## 3.3 Job Workflow

01 — Job Created

02 — Waiting for Documents

03 — Documents Received

04 — Accountant Processing

05 — Supervisor Review

06 — Awaiting Client Signature

07 — Ready for Lodgement

08 — Lodged

09 — Completed

Additional states: ON HOLD and ACTION REQUIRED.

## 3.4 Internal vs Client-Facing Status

Internal statuses can contain operational detail.

Client-facing statuses must use simple, professional wording.

Create a mapping table: Internal Status → Client Status → Client Message → Notification Trigger.

Internal notes, staff comments and review comments must never be exposed to the client.

## 3.5 Staff Dashboard

Display Client, Job, Accountant, Supervisor, Status, Days in Stage and Next Action.

Filters: Accountant, Supervisor, Job Type, Status, Overdue, Action Required and Waiting for Client.

Search by client name, entity or job.

Ability to open a job directly from the dashboard.

Clear visual indicators for jobs sitting too long in one stage.

## 3.6 Supervisor Queue

Dedicated list of jobs currently at Supervisor Review.

Oldest jobs visible first or sortable by age.

Approve action moves job to Awaiting Client Signature.

Return/reject action moves job back to Accountant Processing and records an internal reason.

Approval/rejection action must be written to audit history.

## 3.7 Client Portal

Client sees current jobs.

For each job: client-facing status, progress indicator, last updated date, next action and outstanding items.

Client can securely upload requested documents.

Portal must work cleanly on mobile without needing a native app.

Client can see whether action is required from them or whether Elite is currently handling the job.

## 3.8 Document Upload

Allow PDF, JPG/JPEG, PNG, Word and Excel. HEIC support if practical.

Allow camera/photo upload from mobile browser.

Every document must be tied to Client → Entity → Job → Document.

Capture file name, uploader, upload date/time and document category.

Document categories: Income, PAYG, Rental Property, Investments, Shares, Crypto, Business, Motor Vehicle, Expenses, Superannuation, Private Health, Bank Statements, Previous Tax Documents and Other.

## 3.9 Outstanding Documents

Staff can create an outstanding-document request and optionally set a due date.

Client sees the request prominently as Action Required.

Client can upload directly against the request.

Staff can mark an item received/completed.

The job should clearly show how many outstanding items remain.

## 3.10 Notifications

Automatic email notification for selected status changes.

Messages should be template-based and editable by an administrator.

Log whether a notification was sent, failed or was resent.

No duplicate notification should be sent when a user simply edits unrelated job information.

Phase 1 standard messages: Documents Received, Supervisor Review, Action Required, Awaiting Signature, Lodged and Completed.

## 3.11 Audit Trail

Log creation of job.

Log staff assignment changes.

Log every workflow status change.

Log client uploads.

Log outstanding-document requests and completion.

Log notifications sent and failed.

Log supervisor approvals/returns.

Audit events should display user, timestamp and action.

## 3.12 Administration

Create, edit and disable users.

Assign staff roles.

Assign accountants and supervisors.

Manage notification templates.

View notification logs and audit logs.

Resend failed or selected notifications.

Basic ability to create/edit job types and client-facing labels without code changes where practical.

# 4. Phase 1 — Two-Week Delivery Plan

Delivery rule: No additional feature should be allowed to jeopardise the two-week launch. Anything outside the MVP acceptance criteria moves to Phase 2 or the post-MVP backlog.

| Day | Date | Engineer Work | Required Output |
| --- | --- | --- | --- |
| Day 1 | Mon 7 Sep | Finalise architecture, database entities, roles, workflow states, client-facing status mapping and screen wireframes. Confirm what is in/out of Phase 1. | Approved technical design + data model |
| Day 2 | Tue 8 Sep | Build authentication, users, roles/permissions, client records, entities and client-entity relationships. | Secure login + client/entity base |
| Day 3 | Wed 9 Sep | Build jobs, staff assignment, workflow engine, status changes, timestamps and audit events. | End-to-end job object working |
| Day 4 | Thu 10 Sep | Build staff dashboard, search and filters. Add days-in-stage calculation and action-required views. | Usable staff work queue |
| Day 5 | Fri 11 Sep | Build supervisor review queue, approve/return actions and internal notes. Complete first end-to-end internal workflow test. | Internal MVP works start-to-finish |
| Day 6 | Mon 14 Sep | Build client portal: login, job card, progress display, current status, last update, next action and mobile responsive layout. | Client can see job progress |
| Day 7 | Tue 15 Sep | Build document upload, categories, job/entity association and outstanding-document requests. | Client upload + outstanding docs |
| Day 8 | Wed 16 Sep | Build email notification engine, templates, trigger mapping, send/fail logs and duplicate-prevention logic. Add SMS if ready without delaying launch. | Automatic client notifications |
| Day 9 | Thu 17 Sep | Security/permissions QA, mobile QA, failed upload testing, password reset, notification failure testing, audit trail review and bug fixing. | Release candidate |
| Day 10 | Fri 18 Sep | Run full acceptance test with dummy clients/jobs, fix launch blockers, prepare short staff guide and deploy Phase 1 for controlled Elite pilot. | Phase 1 MVP deployed |

# 5. Phase 1 — Acceptance Test / Definition of Done

A client can securely log in and can only see their own records.

A staff member can create or open a client, select the correct entity and create a tax job.

A job can be assigned to an accountant and supervisor.

A job can move through every Phase 1 workflow status without data loss.

The client sees the correct simplified status rather than internal notes.

The client can upload a document from desktop and mobile.

The uploaded document appears against the correct client/entity/job.

Staff can create an outstanding-document request and the client can see and satisfy it.

Selected status changes trigger the correct email automatically.

No duplicate email is created by unrelated job edits.

The supervisor can approve or return a job from the supervisor queue.

The audit trail shows who performed each critical action and when.

The staff dashboard can be filtered by staff member, status and action required.

The portal and dashboard are usable on common desktop and mobile screen sizes.

Ten complete dummy tax jobs can be run from Job Created to Completed without a critical failure.

# 6. Phase 1 — Engineer Deliverables

Working deployed MVP.

Source code stored in Elite-controlled repository.

Environment/configuration documentation.

Database schema/data model documentation.

List of external services and recurring costs used by the system.

Admin credentials and recovery process controlled by Elite.

Basic backup and restore approach documented.

Short staff operating guide.

Known issues / Phase 2 backlog list.

Confirmation that Phase 1 client data is logically segregated and permissions have been tested.

# 7. Phase 1 — Explicitly Out of Scope

Native iOS or Android app.

Full Xero Tax automation/integration.

AI document classification or OCR workflow.

AI tax advice or tax-return preparation.

WhatsApp AI assistant.

Automated document chasing schedules.

E-signature automation.

Advanced management analytics.

Commercial multi-firm/SaaS functionality.

PHASE 2

Full Future Scope — No Timeframe Assigned Yet

# 8. Phase 2 — Purpose

Phase 2 turns the Phase 1 workflow portal into an intelligent automation platform. The Phase 1 database, job workflow, client portal, audit trail and permissions should therefore be designed so these features can be added without rebuilding the core system.

## 8.1 Xero / Xero Tax Integration

Investigate current authorised Xero and Xero Tax integration/API options.

Determine what can be read, written or synchronised for client/entity/job/tax return information.

Where supported, synchronise client and entity details to avoid duplicate entry.

Where supported, detect relevant tax job/lodgement events and update Elite Client Hub automatically.

Create clear exception handling when external systems are unavailable or data does not match.

Avoid brittle screen scraping or unsupported methods for confidential tax information.

## 8.2 AI Document Intake & Classification

Automatically analyse uploaded receipts and documents.

Identify likely document type, merchant/source, date, amount and category where relevant.

Rename files consistently.

Suggest entity/job/category placement.

Allow staff to accept, edit or reject AI classification.

Retain original file and audit the AI suggestion versus final staff decision.

## 8.3 Intelligent Job Checklists

Create document/checklist templates by job type.

Generate expected information when a job is created.

Compare documents received against expected items.

Show missing items to staff and clients.

Allow manual override because not every checklist item applies to every client.

## 8.4 Automated Client Chasing

Automated reminder sequence for outstanding items.

Configurable reminder intervals and escalation rules.

Automatically stop reminders when the requested item is received.

Allow staff to pause or cancel reminders for a client/job.

Maintain full communication log.

## 8.5 WhatsApp Integration

Connect approved WhatsApp business messaging capability.

Send selected job progress notifications through WhatsApp.

Allow clients to ask simple status questions.

Retrieve answers only from the client’s actual job record.

Use appropriate identity/authentication controls before disclosing sensitive information.

Allow handoff to staff when a question cannot safely be automated.

## 8.6 AI Client Status Assistant

Answer “Where is my return?”, “What do you still need?” and similar operational questions.

Explain current stage in plain language.

Provide next action and outstanding-item summary.

Never invent a status when data is missing; escalate to staff instead.

## 8.7 AI Staff Assistant

Summarise the current job.

Summarise communication history.

Identify outstanding documents.

Answer who last acted and when.

Highlight jobs with no progress for a defined period.

Generate draft client follow-ups for staff review.

## 8.8 AI Supervisor Review Assistance

Generate a pre-review job summary for supervisor.

Summarise documents received and outstanding items.

Highlight significant changes versus prior year where data is available.

Flag unusual or potentially high-risk items for human review.

Keep the accountant/supervisor responsible for final tax decisions; AI provides assistance only.

## 8.9 E-Signature Integration

Generate or route approved documents for electronic signature.

Automatically update job status to Awaiting Client Signature.

Detect signature completion through authorised integration/webhook where possible.

Update job to Signed / Ready for Lodgement and notify relevant staff.

Archive signed documents against the correct job.

## 8.10 Appointment / Setmore Integration

Allow client to book from within portal.

Display upcoming relevant appointments.

Link appointment to client/entity/job where possible.

Allow automated reminders and internal visibility.

## 8.11 Advanced Notification Channels & Preferences

Client-selectable communication preference: email, SMS and/or WhatsApp where appropriate.

Quiet hours and non-urgent communication settings.

Notification templates by job type and stage.

Escalation when messages repeatedly fail.

## 8.12 Management Analytics

Active jobs by stage.

Average turnaround time.

Average days in each stage.

Jobs waiting on client.

Jobs awaiting supervisor.

Jobs overdue or stagnant.

Jobs completed by accountant and team.

Document request ageing.

Client notification volume and delivery success.

Reduction in routine status enquiries as a key success KPI.

## 8.13 Workflow Automation & Recurring Jobs

Automatically create recurring annual/quarterly jobs where appropriate.

Pre-populate workflow/checklists from prior work.

Assign jobs by team/workload rules where desired.

Automatically move or queue work based on validated trigger events.

Add exception queue for cases requiring human intervention.

## 8.14 Security, Privacy & Governance Upgrade

Multi-factor authentication.

Encryption and key-management review.

Granular permission review.

Data-retention and deletion controls.

Download/export audit capability.

Security monitoring and alerting.

Backup, restore and disaster-recovery testing.

Formal privacy/security review before broad deployment or commercialisation.

## 8.15 Commercialisation Readiness (Optional Later Layer)

Assess whether the Elite system can become a product for other accounting practices.

Multi-firm tenancy architecture.

Firm branding and configurable workflows.

Subscription/billing model.

Firm-level admin and permissions.

Usage analytics and support tooling.

Onboarding/migration process for external firms.

# 9. Phase 2 — Overall Target Operating Model

Client/job created

Document checklist generated

Client uploads documents

AI classifies and organises uploads

Missing information is identified and requested

Automated reminders continue until requirements are satisfied

Accountant prepares work

Supervisor receives review task and AI review summary

Client receives progress updates automatically

Documents are sent for e-signature

Signature completion updates the workflow

Tax return is lodged

Xero/Xero Tax event updates the job automatically where supported

Client is notified

Final documents are stored

Job is completed

Future recurring job is scheduled/generated where appropriate

# 10. Engineering Principles for Both Phases

Build Phase 1 for speed, but do not create a dead-end architecture.

Prefer secure, supported APIs and webhooks over manual scraping or fragile browser automation.

Keep workflow logic separate from the user interface so additional channels and integrations can be added later.

Use clear event logging so every automatic action can be traced.

Never allow AI to silently make or lodge professional tax decisions.

Use human approval gates for sensitive or consequential actions.

Design for mobile web first; a native app is optional, not a prerequisite.

Keep the staff workflow simpler than the current process. The software must reduce clicks and chasing rather than create more administration.

Elite must retain control of source code, credentials, production data and third-party accounts.

# 11. Phase 1 Priority Statement for the Engineer

The two-week goal is not to build the final platform. It is to build one reliable workflow that solves the immediate operational problem: every staff member and every client can see where the job is, what is holding it up, who needs to act next, and the client is informed automatically. If a feature does not materially help achieve that outcome, it must not delay the Phase 1 launch.